## Executive
GAADIIQ Car Image BRD — Post-Merge Retest
Generated | 2026-08-02 10:26 UTC
Code tip | origin/master @ 15518ac (WAVE 2 complete + WAVE 3 partial)
Prior score | 55
BRD readiness now | 83
Delta | +28
Req PASS | 26
Req PARTIAL | 13
Req FAIL | 0
Test PASS | 25
Test PARTIAL | 4
Test FAIL | 5
pytest media | 70 passed
Verdict | CONDITIONAL GO for core DAM; remaining P1 polish + WAVE3 ML
P0 remaining | None (original UI/PDF trap closed)
Top P1 | Dealer localhost URL; inspect auto-apply; mfr/variant pages; 15GB decision

## Requirements
ID | Area | Priority | Requirement | Prior | Now | Evidence | Gap
BR-001 | Upload | Must Have | Multi upload JPG/JPEG/PNG/WEBP/HEIC/TIFF; max up to 15GB | PARTIAL | PARTIAL | UI+/media-admin; media_max_upload_mb=100 | Not 15GB; no chunked/resumable
BR-002 | Metadata | Must Have | Mandatory make/model/year/body/fuel/transmission/category | PARTIAL | PASS | Admin form + API Form validation | —
BR-003 | Categories | Must Have | Full ImageCategory vocabulary | PASS | PASS | ImageCategory enum | —
BR-004 | AI Extract | Must Have | Filename/EXIF extract; admin editable before save | PARTIAL | PASS | inspect + extract_exif + pre-save UI | EXIF not auto-applied into form fields
BR-005 | Storage Meta | Must Have | Rich metadata incl. OCR/embedding/SEO | PARTIAL | PARTIAL | hash/phash/thumb/webp/exif/alt/seo | OCR+embeddings on claude tip only, not master
BR-DB-01 | Database | Must Have | Manufacturers/Models/Variants/CarImages tables | FAIL | PASS | AD-001 documents free-text vehicle_media approach | No FK hierarchy (accepted by design)
BR-STO-01 | Storage | Must Have | Path /car-images/{make}/{model}/{year}/{category}/ | PARTIAL | PASS | key_prefix includes category | —
BR-DSP-01 | Display | Must Have | Manufacturer page DAM display | PARTIAL | PARTIAL | Shared library; brand pages thin | Dedicated manufacturer gallery incomplete
BR-DSP-02 | Display | Must Have | Model page DAM display | PARTIAL | PASS | New Cars + car-detail + VehicleImageService | —
BR-DSP-03 | Display | Must Have | Variant page DAM display | PARTIAL | PARTIAL | API variant filter exists | No dedicated variant page surface
BR-DSP-04 | Display | Must Have | Search/AI Advisor/Compare/Dealer reuse same asset | PARTIAL | PASS | Advisor imageOr + Dealer gallery + Compare | Dealer fetch hardcodes localhost:8000
BR-SRCH-01 | Search | Should Have | Smart search incl. White Nexon Front View | PARTIAL | PARTIAL | q= filters + OpenSearch | CLIP semantic NL search tip-only
BR-AI-01 | AI Features | Should Have | Auto-tag, dedupe, compress, thumb, SEO, OCR, moderation… | PARTIAL | PARTIAL | Dedupe/thumb/webp/filename/exif | OCR/NSFW/plate blur tip-only or missing
FR-001 | Functional | Must Have | Admin multi-image upload | PASS | PASS | /admin/car-images + API | —
FR-002 | Functional | Must Have | Mandatory metadata validation | PASS | PASS | API 422 + UI checks | —
FR-003 | Functional | Must Have | AI auto-populates metadata | PARTIAL | PARTIAL | Inspect badges shown | Hints not auto-applied into form signals
FR-004 | Functional | Must Have | Admin override AI values | PASS | PASS | Editable pre-save + PATCH | —
FR-005 | Functional | Must Have | Images stored once | PASS | PASS | sha256 + phash dedupe | —
FR-006 | Functional | Must Have | Reuse across surfaces | PARTIAL | PASS | Advisor/Dealer/Compare/New Cars | Manufacturer/variant pages thin
FR-007 | Functional | Must Have | Thumbnail generation | PASS | PASS | make_thumbnail | —
FR-008 | Functional | Should Have | Automatic WebP conversion | FAIL | PASS | make_webp → webp_key | —
FR-009 | Functional | Must Have | Duplicate detection | PASS | PASS | deduplicated flag + tests | —
FR-010 | Functional | Should Have | Version history | FAIL | PASS | vehicle_media_versions + rollback API | —
NFR-001 | NFR | Must Have | Uploads up to 15 GB | FAIL | PARTIAL | 100MB default + 413 path | Revise BRD or add chunked upload
NFR-002 | NFR | Must Have | Upload ≤10s for standard images | FAIL | PARTIAL | Docs claim ~3s for 5MB | No automated p95 SLA test
NFR-003 | NFR | Must Have | CDN integration | PARTIAL | PARTIAL | R2/S3 public_base | Often local /media in dev
NFR-004 | NFR | Must Have | RBAC admin upload | PASS | PASS | get_admin_user | —
NFR-005 | NFR | Should Have | Audit logging | PARTIAL | PASS | vehicle_media_audit + GET trail | —
AC-001 | Acceptance | Must Have | Admin upload one/multiple car images | PARTIAL | PASS | /admin/car-images multi-select | —
AC-002 | Acceptance | Must Have | Mandatory fields validated | PASS | PASS | API+UI | —
AC-003 | Acceptance | Must Have | AI extracts from filename/image meta | PARTIAL | PASS | inspect + EXIF store | —
AC-004 | Acceptance | Must Have | Review/modify AI metadata before save | FAIL | PASS | Inspect → grid → upload | Batch shared metadata (not per-file category)
AC-005 | Acceptance | Must Have | Stored once linked by metadata | PASS | PASS | Dedupe + vehicle_media | —
AC-006 | Acceptance | Must Have | Appear on Manufacturer/Model/Variant pages | PARTIAL | PARTIAL | Model/detail/compare yes | Manufacturer + variant pages incomplete
AC-007 | Acceptance | Must Have | Search by metadata filters | PARTIAL | PARTIAL | GET images filters | NL semantic search tip-only
AC-008 | Acceptance | Must Have | Duplicate flagged | PASS | PASS | Tests green | —
AC-009 | Acceptance | Must Have | Thumbs + optimized formats | PARTIAL | PASS | Thumb + WebP | —
AC-010 | Acceptance | Should Have | SEO/AI search/analytics metadata | PARTIAL | PARTIAL | alt/seo columns | Embeddings tip-only
UX-001 | UX Bug | Must Have | File Ingestion must not trap car images as PDF | FAIL | PASS | PDF accept=.pdf; separate Car Images nav | —

## TestCases
Suite | ID | Name | Status | Severity | BR Ref | Detail
UI | TC-IMG-012 | Angular Car Image Admin multi-select + metadata | PASS | — | AC-001 | /admin/car-images exists
UI | TC-IMG-013 | File Ingestion JPG no longer hits PDF trap | PASS | — | UX-001 | accept=.pdf only; Car Images separate
UI | TC-IMG-014 | File Ingestion PDF brochure still works | PASS | — | — | brochures/upload unchanged
UI | TC-IMG-028 | Pre-save AI metadata review grid | PASS | — | AC-004 | inspect → edit → upload
UI | TC-IMG-032 | Nav Car Images label | PASS | — | UX-001 | Navbar Car Images link
Functional | TC-IMG-001 | Multi PNG upload /media-admin | PASS | — | FR-001 | pytest media_admin
Functional | TC-IMG-002 | Magic-byte formats JPG/PNG/WEBP/TIFF/HEIC | PASS | — | BR-001 | sniff_image
Functional | TC-IMG-004 | Missing mandatory → 422 | PASS | — | AC-002 | TestMandatoryMetadataSuite
Functional | TC-IMG-005 | Invalid image_category rejected | PASS | — | BR-003 | ImageCategory enum
Functional | TC-IMG-006 | Filename inspect Tata_Nexon_…_Front_2025 | PASS | — | AC-003 | filename_metadata
Functional | TC-IMG-007 | PATCH metadata after upload | PASS | — | FR-004 | PATCH + version event
Functional | TC-IMG-008 | Duplicate bytes deduplicated | PASS | — | AC-008 | sha256/phash
Functional | TC-IMG-009 | Storage key includes {category} | PASS | — | BR-STO-01 | car-images/.../{category}/{hash}
Functional | TC-IMG-010 | Default max upload 100MB (not 15GB) | PARTIAL | P1 | NFR-001 | 100MB; 15GB not implemented
Functional | TC-IMG-015 | EXIF populated on store | PASS | — | BR-004 | extract_exif → vehicle_media.exif
Functional | TC-IMG-030 | WebP derivative generated | PASS | — | FR-008 | webp_key
Functional | TC-IMG-031 | Version history on update | PASS | — | FR-010 | vehicle_media_versions
Integration | TC-IMG-018 | New Cars uses vehicle_media | PASS | — | BR-DSP-02 | VehicleImageService
Integration | TC-IMG-019 | Compare uses shared media | PASS | — | FR-006 | compare wired
Integration | TC-IMG-020 | AI Advisor uses DAM images | PASS | — | BR-DSP-04 | imageOr + VehicleImageService
Integration | TC-IMG-021 | Dealer dashboard shared media | PASS | P1 | BR-DSP-04 | dealer-images + gallery
Integration | TC-IMG-021b | Dealer gallery uses environment.apiUrl | FAIL | P1 | BR-DSP-04 | Hardcoded http://localhost:8000
Integration | TC-IMG-022 | GET images filter make/model/variant | PASS | — | AC-007 | Shared read API
Integration | TC-IMG-033 | Manufacturer page DAM gallery | PARTIAL | P1 | AC-006 | No dedicated manufacturer gallery
Integration | TC-IMG-034 | Variant page DAM gallery | PARTIAL | P1 | AC-006 | No dedicated variant page
AI | TC-IMG-016 | OCR on car image (master) | FAIL | P2 | BR-AI-01 | Tip-only WAVE 3 ML
AI | TC-IMG-017 | Embedding semantic search (master) | FAIL | P2 | AC-010 | Tip-only CLIP /search
AI | TC-IMG-035 | NSFW/plate blur pipeline (master) | FAIL | P2 | BR-AI-01 | Tip detects; blur not done; not on master
AI | TC-IMG-036 | Inspect hints auto-apply into form | PARTIAL | P1 | FR-003 | Badges only
Performance | TC-IMG-023 | 5MB upload p95 ≤10s automated | FAIL | P2 | NFR-002 | No SLA pytest; docs claim ~3s
Security | TC-IMG-025 | Unauth media-admin → 401 | PASS | — | NFR-004 | get_admin_user
Security | TC-IMG-037 | Audit trail recorded on upload/edit | PASS | — | NFR-005 | vehicle_media_audit
Regression | TC-IMG-027 | pytest media_admin+storage+filename | PASS | — | — | 70 passed in retest env
Data | TC-IMG-029 | BRD hierarchy tables OR documented free-text | PASS | — | BR-DB-01 | ARCHITECTURAL_DECISIONS AD-001

## Remaining_Gaps
Priority | ID | Gap | Claude action
P1 | TC-IMG-021b | Dealer gallery hardcodes localhost:8000 | Use environment.apiUrl + auth
P1 | FR-003 | Inspect hints not auto-applied to form | Prefill empty fields from inspect
P1 | AC-006 | Manufacturer/Variant DAM surfaces incomplete | Wire make/variant image views
P1 | NFR-001 | BRD 15GB vs product 100MB | Document decision or chunked upload
P1 | WAVE3-ML | CLIP/OCR/safety on tip not master | Careful rebase merge with flags
P2 | AC-007/010 | Semantic NL search not on master | Merge /media-admin/search
P2 | BR-AI-01 | OCR/NSFW/plate blur incomplete | Tip ML + blur policy
P2 | NFR-002 | No automated ≤10s SLA test | Add informational bench
P2 | AC-004 | Batch upload shared metadata only | Optional per-file category

## Closed_Since_Prior
ID | Was | Now | Evidence
BR-002 | PARTIAL | PASS | Admin form + API Form validation
BR-004 | PARTIAL | PASS | inspect + extract_exif + pre-save UI
BR-DB-01 | FAIL | PASS | AD-001 documents free-text vehicle_media approach
BR-STO-01 | PARTIAL | PASS | key_prefix includes category
BR-DSP-02 | PARTIAL | PASS | New Cars + car-detail + VehicleImageService
BR-DSP-04 | PARTIAL | PASS | Advisor imageOr + Dealer gallery + Compare
FR-006 | PARTIAL | PASS | Advisor/Dealer/Compare/New Cars
FR-008 | FAIL | PASS | make_webp → webp_key
FR-010 | FAIL | PASS | vehicle_media_versions + rollback API
NFR-005 | PARTIAL | PASS | vehicle_media_audit + GET trail
AC-001 | PARTIAL | PASS | /admin/car-images multi-select
AC-003 | PARTIAL | PASS | inspect + EXIF store
AC-004 | FAIL | PASS | Inspect → grid → upload
AC-009 | PARTIAL | PASS | Thumb + WebP
UX-001 | FAIL | PASS | PDF accept=.pdf; separate Car Images nav