## Executive
GAADIIQ Mobile Production QA
Generated | 2026-07-21T07:03:26.229152+00:00
Production Readiness | 22
Overall Quality | 48
Feature Coverage % | 50
Recommendation | NO-GO
Blockers | 4
Critical | 8
High | 10
Medium | 11
Low | 7
Issues Total | 40

## Issues
ID | Severity | Area | Screen | Category | Problem | Root Cause | Expected | Files
MOB-001 | BLOCKER | Platform | iOS | Missing Feature | No iOS Capacitor project exists; only Android WebView shell under apps/gaadiiq-angular/android. | Product scoped Android-only scaffold; ios/ directory never created. | Parity iOS app (Xcode project) with same Capacitor webDir and App Store readiness. | apps/gaadiiq-angular/capacitor.config.ts; apps/gaadiiq-angular/package.json
MOB-002 | BLOCKER | Architecture | Auth (all) | Security/Architecture | Dual auth stacks: Angular uses Supabase Auth; FastAPI uses RS256 JWT. Mobile UI does not obtain FastAPI tokens, so many API routes (payments, loans inquiries, notifications, diagnosis history) are unreachable or broken from the app. | Two parallel backends evolved without a unified session bridge. | Single identity: either Supabase JWT validated by API, or mobile uses FastAPI login and stores secure tokens. | apps/gaadiiq-angular/src/app/services/auth.service.ts; apps/api/core/security.py; apps/gaadiiq-angular/src/app/services/api.service.ts
MOB-003 | BLOCKER | Payments | Pricing Plans / Feature Listing | Missing Feature | No Razorpay checkout wired in Angular despite API /payments/* and marketing copy claiming UPI/cards/EMI via Razorpay. | Payments implemented server-side only; pricing-plans is FAQ/static. | End-to-end checkout: create order → Razorpay SDK → verify → unlock plan/listing. | apps/gaadiiq-angular/src/app/pages/pricing-plans/; apps/api/routers/payments.py
MOB-004 | BLOCKER | Mobile Native | App shell | Architecture | Capacitor app is a bare WebView wrap: no Camera, Geolocation, Push, Preferences, or Filesystem plugins; package.json has no cap sync/run scripts. | Only @capacitor/core + android installed. | Native plugins for camera, location, push, secure storage; npm scripts for sync/build. | apps/gaadiiq-angular/package.json; apps/gaadiiq-angular/capacitor.config.ts; apps/gaadiiq-angular/android/app/capacitor.build.gradle
MOB-005 | CRITICAL | Security | AndroidManifest | Security | android:allowBackup="true" allows ADB backup of WebView data including localStorage (wishlist, journey, possibly session fragments). | Default Capacitor manifest not hardened. | allowBackup=false; exclude sensitive paths; disable cleartext. | apps/gaadiiq-angular/android/app/src/main/AndroidManifest.xml
MOB-006 | CRITICAL | Security | Network | Security | No SSL/certificate pinning and no Network Security Config; MITM on user devices possible for API/Supabase traffic. | No pinning library or network_security_config.xml beyond defaults. | Pin api.gaadiiq.com + Supabase host; fail closed on mismatch in release builds. | apps/gaadiiq-angular/android/app/src/main/res/xml/; apps/gaadiiq-angular/capacitor.config.ts
MOB-007 | CRITICAL | Security | AI Diagnosis API | Security | GET /diagnosis/{id} is unauthenticated → IDOR: anyone with UUID can read another user's diagnosis (vehicle + symptoms). | get_diagnosis has no Depends(get_current_user) or ownership check. | Require auth; allow owner or admin only. | apps/api/routers/diagnosis.py
MOB-008 | CRITICAL | Security | AI modules | AI/Security | User-controlled text interpolated into LLM prompts with no sanitisation/injection fence — prompt injection risk; HLD claims sanitisation but code lacks it. | f-string prompt assembly in diagnosis.py / valuation.py / sentiment.py. | Input length limits, delimiter fencing, instruction hierarchy, output schema validation, refusal tests. | apps/api/services/diagnosis.py; apps/api/services/valuation.py; apps/api/services/sentiment.py
MOB-009 | CRITICAL | Auth | Registration / Login | Missing Feature | OTP / phone SMS authentication does not exist. Register may collect phone but AuthService.register() never uses verifyOtp. | Email/password + OAuth only. | Phone OTP via Supabase or MSG91/Twilio for India primary mobile UX. | apps/gaadiiq-angular/src/app/pages/register/; apps/gaadiiq-angular/src/app/services/auth.service.ts
MOB-010 | CRITICAL | Permissions | City / Diagnosis geolocation | Security/Mobile | App uses navigator.geolocation but AndroidManifest declares only INTERNET — no ACCESS_FINE_LOCATION / COARSE. | Web API used without native permission declarations/plugins. | Add permissions + @capacitor/geolocation with runtime prompts. | apps/gaadiiq-angular/android/app/src/main/AndroidManifest.xml; apps/gaadiiq-angular/src/app/components/city-selector/
MOB-011 | CRITICAL | Auth Bridge | API calls | API | ApiService.submitLoanInquiry hits /loans/inquiry but API exposes /loans/inquiries — broken loan lead capture. | Path typo / contract drift. | Align client path; add contract test. | apps/gaadiiq-angular/src/app/services/api.service.ts; apps/api/routers/loans.py
MOB-012 | CRITICAL | RBAC | Dealer/Admin | Security | sellerGuard is client-side only. FastAPI dealer endpoints use soft Dealer-row checks; any user can POST /dealers/register. Role enums diverge (seller vs dealer). | No unified server-side role enforcement aligned with Angular. | Unified roles; require_role on sensitive routes; adminGuard. | apps/gaadiiq-angular/src/app/guards/seller.guard.ts; apps/api/routers/dealers.py; apps/api/core/dependencies.py
MOB-013 | HIGH | Features | Insurance | Missing Feature | No insurance enquiry API or partner quote flow; only client-side premium estimates / marketing. | PRD/LLD endpoints never implemented. | POST insurance lead + partner deep-links with disclosure. | apps/api/routers/; apps/gaadiiq-angular/src/app/pages/car-detail/
MOB-014 | HIGH | Features | AI Chat | Missing Feature / AI | Ask GAADIIQ / POST /recommend/ai-chat (SSE) from LLD is not implemented. | Recommend is quiz/rules only. | Streaming chat endpoint + mobile UI with citations/fallback. | apps/api/routers/; apps/gaadiiq-angular/src/app/pages/ai-advisor/
MOB-015 | HIGH | Features | Push Notifications | Missing Feature | No FCM/APNs Capacitor push plugin; in-app notifications API unused by primary Supabase auth path. | Push never integrated. | FCM + user tokens; deep links to bookings/price drops. | apps/gaadiiq-angular/android/; apps/api/routers/notifications.py
MOB-016 | HIGH | AI Advisor | /ai-advisor | AI | Angular advisor uses local heuristic scoring; not wired to POST /recommend. Diverges from Next.js advisor. | Client-only engine shipped as AI. | Call API; method badge; unify scoring; use CityService. | apps/gaadiiq-angular/src/app/pages/ai-advisor/ai-advisor.component.ts; apps/api/routers/recommend.py
MOB-017 | HIGH | Data | Wishlist / Price Alerts / Reviews | Reliability | Wishlist, price alerts, recently viewed persist only in localStorage — lost on reinstall, not cross-device. | Offline-first shortcuts without sync layer. | Authenticated CRUD against API; local cache as offline mirror. | apps/gaadiiq-angular/src/app/pages/used-cars/; apps/gaadiiq-angular/src/app/pages/price-alerts/
MOB-018 | HIGH | Uploads | List Car / Diagnosis | Security | Audio/video/document upload unsupported. List-car uses Cloudinary unsigned preset (abuse risk). Upload MIME allowlist only; vision may fetch arbitrary image_urls (SSRF). | No magic bytes/AV; unsigned Cloudinary; unrestricted vision URLs. | Magic bytes, size caps, AV scan, signed uploads, SSRF allowlist. | apps/api/routers/upload.py; apps/api/services/vision.py; apps/gaadiiq-angular/src/app/services/cloudinary.service.ts
MOB-019 | HIGH | Rate Limit | API | Security/Performance | SlowAPI rate limits disabled unless environment==production; diagnosis/analyse not limited; /metrics public. | Limiter gated; incomplete decoration. | Enable limits in staging; rate-limit diagnosis; protect /metrics. | apps/api/core/limiter.py; apps/api/routers/diagnosis.py; apps/api/main.py
MOB-020 | HIGH | Database | Intent / Diagnosis models | Database | customer_activities/intent_scores FK columns String(36) vs UUID PKs; vehicle_diagnoses.user_id nullable without FK. | Migration type mismatch in 0005/0006. | UUID FKs with ON DELETE SET NULL/CASCADE; backfill. | apps/api/alembic/versions/0005_customer_intent_tables.py; apps/api/alembic/versions/0006_vehicle_diagnosis.py
MOB-021 | HIGH | CORS | API | API | Default allowed_origins is localhost:3000; Capacitor/Android and Angular :4200 may be blocked against production API. | CORS not listing mobile/web production origins. | Explicit allowlist: web, capacitor origins, staging. | apps/api/main.py; apps/api/core/config.py
MOB-022 | HIGH | Testing | Mobile QA | Quality | Only 1 Angular unit spec (boilerplate broken); no Appium/Detox against Capacitor; Android instrumented tests still Capacitor sample package names. | No mobile test strategy executed. | Contract tests + critical-path Appium; fix sample tests; CI on PR. | apps/gaadiiq-angular/src/app/app.component.spec.ts; apps/gaadiiq-angular/android/app/src/androidTest/
MOB-023 | MEDIUM | UX | Used Cars Budget Slider | UI/UX | Dual-range slider: WebKit thumb misalignment (no margin-top), no z-index swap when thumbs overlap, track not clickable. | CSS dual-range incomplete. | Centered thumbs, dynamic z-index, accessible labels. | apps/gaadiiq-angular/src/app/pages/used-cars/used-cars.component.scss
MOB-024 | MEDIUM | UX | Used Cars | UI/UX | showAllIndiaBanner requires !allIndiaOverride so amber banner never shows after auto-override for empty cities. | Inverted banner condition. | Show banner when override active. | apps/gaadiiq-angular/src/app/pages/used-cars/used-cars.component.ts
MOB-025 | MEDIUM | Features | New Cars | Functional | New Cars P0 fixes (Above ₹30L applyBudget) live on cursor/fix-new-cars-module-85e1 and are NOT merged into Claude tip. | Unmerged fix branch. | Merge/cherry-pick fix branch. | apps/gaadiiq-angular/src/app/pages/new-cars/
MOB-026 | MEDIUM | Features | EV / TCO | Missing Feature | No dedicated EV calculator screen; TCO service exists but weak mobile discovery. | Feature incomplete in IA. | EV cost/range calculator page; TCO entry from car detail. | apps/gaadiiq-angular/src/app/services/tco.service.ts
MOB-027 | MEDIUM | Features | Dealer Search / Service History | Missing Feature | No dealer directory search; service booking only opens maps to static SERVICE_CENTERS; no service history. | Diagnosis CTA stub. | Dealer search API+UI; booking persistence; history. | apps/gaadiiq-angular/src/app/pages/vehicle-diagnosis/
MOB-028 | MEDIUM | A11y | Global | Accessibility | Sparse ARIA; many outline:none without :focus-visible; no TalkBack/VoiceOver pass; contrast not systematically verified. | A11y not a release gate. | WCAG 2.2 AA on top flows. | apps/gaadiiq-angular/src/app/**/*.html; apps/gaadiiq-angular/src/styles.scss
MOB-029 | MEDIUM | Performance | Listings / Images | Performance | Listing grids without virtual scroll; no measured startup/FPS/memory on device. | No perf budget in CI. | Virtual scroll, image sizing, WebView metrics. | apps/gaadiiq-angular/src/app/pages/listings/; apps/gaadiiq-angular/ngsw-config.json
MOB-030 | MEDIUM | Offline | Global | Reliability | No true offline mode; SW precaches shell only; forms fail opaquely offline; no queue/retry. | PWA shell ≠ offline product. | Offline banner, queued mutations, read-through cache. | apps/gaadiiq-angular/ngsw-config.json
MOB-031 | MEDIUM | EMI | EMI Calculator | Business Rules | Bank rates are hardcoded stubs; client EMI not using GET /loans/emi-calculator. | Marketing calculator. | Disclose indicative; sync API calculator. | apps/gaadiiq-angular/src/app/pages/emi-calculator/
MOB-032 | MEDIUM | Sentiment | Dealer Dashboard | Security/Privacy | Public sentiment track endpoint forgeable; no customer consent UX. | Privacy/product gap. | Consent, auth-only tracking, disclosure. | apps/api/routers/sentiment.py
MOB-033 | MEDIUM | Compatibility | Devices | Compatibility | minSdk 24 but product asks Android 12+ validation; foldable/tablet/landscape untested; no iPad. | No device matrix execution. | Document and execute supported device matrix. | apps/gaadiiq-angular/android/variables.gradle
MOB-034 | LOW | Code Quality | Android tests | Quality | Instrumented tests still reference com.getcapacitor.myapp / ExampleUnitTest. | Capacitor template leftover. | Replace with GAADIIQ smoke or remove from CI. | apps/gaadiiq-angular/android/app/src/test/; androidTest/
MOB-035 | LOW | UX | Used Cars empty state | UI/UX | No AI Advisor CTA when filters yield 0 results; no URL write-back for filters. | Incomplete empty-state IA. | Advisor link + query sync. | apps/gaadiiq-angular/src/app/pages/used-cars/
MOB-036 | LOW | AI Diagnosis | History | Functional | API /diagnosis/history exists but Angular wizard has no history UI. | UI incomplete. | Past diagnoses list with reopen. | apps/gaadiiq-angular/src/app/pages/vehicle-diagnosis/
MOB-037 | LOW | Security | Root/Jailbreak | Security | No root/jailbreak detection or Play Integrity on release builds. | Not implemented. | Play Integrity / DeviceCheck gated for payments. | apps/gaadiiq-angular/android/
MOB-038 | LOW | Config | Environments | Maintainability | .env.example documents HS256 SECRET_KEY while API uses RS256 PEMs. | Stale docs. | Align examples with JWT key files. | apps/api/.env.example; apps/api/core/config.py
MOB-039 | LOW | Payments Webhook | API | Security | When Razorpay keys unset, webhook verification may be open — dangerous if mis-deployed. | Dev shortcuts. | Fail closed without keys outside local dev. | apps/api/routers/payments.py
MOB-040 | LOW | Profile | Settings | Missing Feature | No dedicated Settings/Profile edit screen; no DPDP delete-account flow. | Thin account IA. | Profile, notification prefs, privacy, delete account. | apps/gaadiiq-angular/src/app/pages/

## Features
Feature | Status | Detail
Registration | PARTIAL | Email/password+OAuth; phone unused; no OTP
Login | PASS | Supabase email/password + Google/Facebook
OTP | FAIL | Not implemented
Password Reset | PASS | resetPasswordForEmail + /reset-password
Dashboard | PARTIAL | Home marketplace, not full role dashboards
Vehicle Search | PASS | Listings/search UI
Compare Cars | PASS | Client compare
Car Details | PASS | /cars/:id
Used Cars | PASS | Filters + inventory (P0 fixed on tip)
AI Recommendation | PARTIAL | Quiz heuristic; not API /recommend
Dealer Search | FAIL | No directory
Dealer Dashboard | PASS | sellerGuard route
Test Drive Booking | PARTIAL | Page exists; Supabase-backed
Loan Calculator | PASS | Client EMI
Insurance | FAIL | No partner flow
EMI Calculator | PASS | /emi-calculator
TCO Calculator | PARTIAL | Service/Next; weak mobile entry
EV Calculator | FAIL | Missing
AI Vehicle Diagnosis | PASS | Wizard + API + fallback
Customer Sentiment | PARTIAL | Dealer API only
AI Chat | FAIL | Not implemented
Vehicle Image Upload | PARTIAL | Cloudinary list-car; diagnosis API upload
Audio Upload | FAIL | Missing
Video Upload | FAIL | Missing
Document Upload | FAIL | Missing
Wishlist | PARTIAL | localStorage
Notifications | PARTIAL | API exists; no push; auth mismatch
User Profile | PARTIAL | Thin
Settings | PARTIAL | Theme/lang only
Service Booking | PARTIAL | Maps to static centres
Service History | FAIL | Missing
Review System | PARTIAL | Mixed local/API
Payment Flow | FAIL | No mobile checkout
Logout | PASS | Supabase signOut
Android | PARTIAL | WebView shell only
iOS | FAIL | No project