## Findings
GAADIIQ — Security Audit
Code audit of apps/api against master @ 2cb3d1c, 3 Sep 2026. Findings come from reading the code, not from a scanner or a penetration test.
Scope: authentication, sensitive-data handling, CORS, payments, uploads, rate limits, logging. NOT covered: dependency CVEs, Supabase row-level security policies, infrastructure, or any live testing.
ID | Area | Finding | Severity | Status | Evidence (file:line) | Impact if exploited | Fix | Owner | Notes / date closed
SEC-01 | Sensitive data | MechanicOut returned the stored PAN in full, not the masked form | High | Fixed | routers/mechanics.py:56 (_to_out); schemas/mechanic.py:81 | Full PAN of every registered mechanic returned to the mechanic and to any admin session, including GET /mechanics which returns up to 200 records in one response. Breaks the stated rule that a PAN is never returned. Risk is onward exposure: logs, caches, browser history, screenshots. | Route through kyc.mask_pan, which already existed. PR #202, 4 tests added. | Claude | Fixed 3 Sep 2026. Confirmed tests fail without the change (3 of 4).
SEC-02 | Auth / config | Five protections all hang on ENVIRONMENT == 'production' being exactly right | Info | Verified OK | core/config.py:360 (is_production); core/dependencies.py:140 | If the variable is unset, misspelt, or cased differently, ALL of these fail silently at once: get_admin_user hands an unauthenticated caller a synthetic Dev Admin; OTPs are logged in plaintext; auth cookies lose the Secure flag; /metrics skips its token check; payments accept without verification. | 1) Confirm ENVIRONMENT=production on the Render dashboard. 2) Consider STRICT_ENVIRONMENT_CHECK=true so a mismatch refuses to boot rather than warning. | Manoj | Confirmed on the Render dashboard 3 Sep 2026: ENVIRONMENT = production. All six dependent protections are live — admin bypass closed, OTP logging raises, cookies Secure, /metrics token enforced, payments verify, rate limiter ENABLED. STRICT_ENVIRONMENT_CHECK still unset, so a future mismatch would warn rather than refuse to boot; that remains a judgement call, not a gap.
SEC-03 | CORS | Origin regex admits any Vercel project whose name starts with 'gaaadiiq' | Low | Open | core/config.py:128 (allowed_origin_regex); main.py:492 | ^https://gaaadiiq[a-z0-9-]*\.vercel\.app$ with allow_credentials=True. Anyone can register a Vercel project named gaaadiiq-anything. Impact is limited: cookies are SameSite=Lax and Supabase tokens live in localStorage, so there is no direct session-riding path — but the rule is wider than the preview URLs it exists to admit. | Tighten to the exact preview pattern Vercel generates for this project. | Manoj | Do this carefully — too tight and the APK and previews fail CORS, which looks like being offline.
SEC-04 | Documentation | schemas/mechanic.py docstring asserted a guarantee the code did not keep | Medium | Fixed | schemas/mechanic.py:1-6 | The file opened by stating that no response model in it could emit a PAN. That was false, and a false assurance is worse than none: it is the reason nobody re-checked the line. Same class of error as the CLAUDE.md notes that once described OpenSearch as deployed. | Fixed as part of SEC-01 — the code now matches the docstring. | Claude | Fixed 3 Sep 2026.
SEC-05 | Aadhaar handling | Aadhaar is validated then discarded; only a peppered digest and last 4 survive | Info | Verified OK | routers/mechanics.py:93-99; services/kyc.py:78 | No gap. Verified because Aadhaar Act s.29(4) makes storing the number an offence for a private entity. There is an explicit `del aadhaar_digits` so nothing below that line can see it. | None. Re-check whenever mechanic or loan KYC changes. | — | Verified 3 Sep 2026.
SEC-06 | Payments | Razorpay HMAC verified with a constant-time comparison, no bypass path | Info | Verified OK | routers/payments.py:99-108 | No gap. hmac.compare_digest, and the verify endpoint has no branch that skips the check. | None. | — | Verified 3 Sep 2026.
SEC-07 | Uploads | Uploads checked by magic bytes, size cap and a per-request file limit | Info | Verified OK | routers/upload.py:90; routers/media_admin.py:57,466 | No gap. Content type is sniffed from the bytes rather than trusted from the client. | None. | — | Verified 3 Sep 2026.
SEC-08 | Rate limiting | Auth, OTP and loan endpoints are rate limited | Info | Verified OK | routers/otp.py:71,81; routers/auth.py:52,78,161,200 | No gap. OTP send is 5/hour, login 5/minute, password reset 3/minute. | Revisit the limiter key if Cloudflare is put in front — see TRUSTED_PROXY_SECRET. | — | Verified 3 Sep 2026.
SEC-09 | Logging | OTP plaintext logging raises in production rather than logging | Info | Verified OK | routers/otp.py:55-58 | No gap. Without MSG91_AUTH_KEY the service refuses to start in production instead of falling back to logging live OTPs. | None — but note this is a sixth thing gated on is_production. See SEC-02. | — | Verified 3 Sep 2026.
SEC-10 | Access control | Loan applications and mechanic records are scoped to their owner or an admin | Info | Verified OK | routers/loan_applications.py:364; routers/mechanics.py:216 | No gap found. Queries filter on current_user.id; the full mechanic record is owner-or-admin only. | None. Re-check when new list endpoints are added. | — | Verified 3 Sep 2026.
Note on I5: Owner and Notes are yours to edit (blue = input). Everything else records what the audit found.

## Pre-launch
Pre-launch checklist
Everything that must be true before real users reach GAADIIQ. Ordered by when it is needed, not by size. Tick the Done column as you go — the Summary sheet counts what is left.
Context: the app is in testing. The Vercel project name is deliberately obscure to keep it out of search results and casual discovery — that is intentional and is NOT a defect. See PL-04.
ID | When | Item | Why it matters | Where to do it | Effort | Done | Notes
PL-01 | Now | Confirm ENVIRONMENT=production on the API service | Five protections collapse together if this string is wrong, and all of them fail silently: the admin dependency hands an unauthenticated caller a synthetic Dev Admin; OTPs get logged in plaintext; auth cookies lose the Secure flag; /metrics skips its token check; payments accept without verification. (SEC-02) | Render dashboard → gaadiiq-api → Environment | 5 min | Yes | Verified on the Render dashboard 3 Sep 2026 — screenshot confirms ENVIRONMENT = production on gaadiiq-api.
PL-02 | Now | Turn on Vercel Deployment Protection | The single highest-value item for keeping people out during testing. Password or Vercel Authentication covers the whole web app including every preview. The project name keeps you out of search results; it does not stop anyone who has the URL. | Vercel → project → Settings → Deployment Protection | 5 min
PL-03 | Now | Close public sign-ups, or require email confirmation | Without this, anyone who reaches the app can create an account and use it. Obscurity does not gate registration. | Supabase → Authentication → Providers / Email | 10 min
PL-04 | At rename | Set ALLOWED_ORIGIN_REGEX anchored to the team slug | The current pattern matches the project-name PREFIX, which anyone can register on Vercel (gaaadiiq-anything.vercel.app matches). Anchor on the team slug at the END instead — that is the part an attacker cannot mint. No code change needed: the env var overrides config.py (verified). (SEC-03) | Render dashboard → gaadiiq-api → Environment | 10 min |  | Deferred deliberately: the regex would hardcode the current project name, which is about to change.
PL-05 | Before users | Decide the API access story | The API is public and CORS does not gate it — CORS only stops browsers on other origins from reading responses; curl ignores it entirely. The APK also carries the production API URL compiled in, so anyone with a build reaches live data. | Cloudflare in front + TRUSTED_PROXY_SECRET / REQUIRE_TRUSTED_PROXY (already built, not switched on) | Half a day |  | docs/CLOUDFLARE.md. Turning the lock on before Cloudflare actually fronts the service refuses every request — a self-inflicted outage. Order matters.
PL-06 | Before users | Confirm MARKETPLACE_ENABLED is off until KYC is ready | Gates listings and KYC. Defaults to False in code; confirm the deployed value matches intent. | Render dashboard | 2 min
PL-07 | Before users | Tell loan applicants what happens next | The lender hand-off is manual by design while payments are pending, and the admin queue is where applications land. If the screen implies a lender is processing it, people wait for a call on an automated timeline that does not exist. | apps/gaadiiq-angular — loan application confirmation screen | 1 hour
PL-08 | Before launch | Add ng test to CI | ci-web.yml runs Playwright but never the unit suite. That is how 13 broken specs sat on master unnoticed, including four guarding a price rule that was wrong on five screens. | .github/workflows/ci-web.yml | 2 hours
PL-09 | Before launch | Resolve the duplicate frontend declaration | render.yaml declares a gaadiiq-web static site while the live web app is on Vercel. Applying that blueprint stands up a second, stale copy on a different URL. | render.yaml | 30 min
PL-10 | Before launch | Generate the release keystore and set the four GitHub secrets | Without them the signed release bundle job stays skipped, so there is no Play Store build. The keystore must be generated by you and never committed. | Local machine + GitHub → Settings → Secrets | 1 hour |  | docs/ANDROID_RELEASE.md. Losing the keystore means never updating the app under the same listing.
PL-11 | Before launch | Apply migration 018 and reconcile the two schema homes | Schema lives in 25 Alembic migrations AND hand-run schema_setup_batch*.sql files. Marketplace and loan tables exist only in the SQL files, so shipping code that needs them does not ship the tables. | Supabase SQL editor + apps/api/alembic | Half a day
PL-12 | Before launch | Fix dark mode contrast failures | About twenty AA failures from hardcoded hexes that predate the theme tokens. e2e/contrast.spec.ts covers light theme only today. | apps/gaadiiq-angular styles | Half a day
PL-13 | Before launch | Run a dependency vulnerability scan | Not covered by the 3 Sep audit at all — no SCA was run against requirements.txt or package-lock.json. | pip-audit / npm audit, or Dependabot | 1 hour
PL-14 | Before launch | Review Supabase row-level security policies | The database enforces its own rules outside this codebase, so the API audit says nothing about them. A permissive policy would bypass every check in FastAPI. | Supabase → Authentication → Policies | Half a day

## Summary
Status at a glance
Counts are formulas over the Findings sheet, so they update as you edit Status and Severity there.
By severity | Pre-launch progress
High | Items total
Medium | Done
Low | Not done
Info | Blocking now
By status
Open
Your call
Fixed
Verified OK
Accepted risk
Needs action
Total findings recorded
Do first
SEC-02 — confirm ENVIRONMENT=production on the Render dashboard. Five protections depend on that one string and all fail silently together if it is wrong. Five minutes.
What this audit did not cover
• Dependency vulnerabilities (no SCA run against requirements.txt or package-lock.json)
• Supabase row-level security policies — the database enforces its own rules outside this codebase
• Any live or penetration testing; every finding comes from reading code
• Infrastructure: Render, Vercel and Cloudflare account and network configuration
• The Angular frontend beyond how it sends credentials

## Method
How to re-run this
So a later review can repeat the checks rather than start over. Each line is what was actually looked at, in the order it was looked at.
# | Check | Where to look | What good looks like
1 | Admin dependency bypass | core/dependencies.py get_admin_user | Outside production it returns a synthetic admin. Confirm production is genuinely production.
2 | What is_production gates | grep -rn 'is_production' apps/api | Every hit is a protection that disappears together. Today: admin, OTP log, cookie Secure, /metrics, payments.
3 | CORS origins | core/config.py allowed_origins, allowed_origin_regex | No wildcard; regex cannot match a domain a third party can register.
4 | Aadhaar never stored | grep -rn 'aadhaar' models/ routers/ services/ | Only digest and last4 columns. The raw value is deleted after hashing.
5 | PAN never returned | grep -rn 'pan_number' routers/ schemas/ | Every response field is masked or a digest. This is where SEC-01 was found.
6 | Payment signature | routers/payments.py _verify_razorpay_signature | hmac.compare_digest, and no branch that skips verification.
7 | Upload validation | routers/upload.py, routers/media_admin.py | Magic-byte sniffing, size cap, per-request file cap.
8 | Rate limits | grep -rn 'limiter.limit' routers/ | Present on auth, OTP, and anything that writes an application.
9 | PII in logs | grep -rn 'logger\.' routers/ ¦ grep -iE 'pan¦aadhaar¦phone¦token' | Nothing logs a secret outside a production guard that raises.
10 | Ownership scoping | grep -rn 'current_user.id' routers/ | Every list and detail read filters by owner or requires admin.