## Summary
GAADIIQ New Cars — Full Feature E2E Retest
2026-07-18 ¦ Angular /new-cars (screenshot features) + API + Next
Suite | PASS | FAIL | PARTIAL | TOTAL
Angular feature E2E (code+CDN probe) | 9 | 13 | 3 | 25
API listing_type=new | 18 | 1 | 0 | 19
Next Playwright suite | 11 | 0 | 0 | 11
Verdict | Angular New Cars page sections RENDER, but E2E feature paths are largely broken: hotlinked images 404 + wrong placeholder path, View Details/Compare/Notify/Budget Above ₹30L/Electric-Luxury body filters miswired, launches/expert content static and inaccurate. API new filter works but seed is empty and km validation missing.

## Angular Feature E2E
ID | Feature / Scenario | Status | Detail | Gap
NC-E2E-001 | Hero By Brand/Budget/Body tabs | PASS | Present in HTML
NC-E2E-002 | Browse by Brand section | PASS | brand-grid + navigateToBrand
NC-E2E-003 | Browse by Body Type section | PASS | 6 cards Hatchback..Luxury
NC-E2E-004 | Browse by Budget section | PASS | 6 budget ranges
NC-E2E-005 | Popular models + filters + sort | PASS | sidebar + sort select
NC-E2E-006 | New Launches carousel | PASS | hardcoded newLaunches
NC-E2E-007 | Upcoming + Notify Me UI | PASS | toggleNotify present
NC-E2E-008 | Expert Recommendations section | PASS | expertPicks hardcoded
NC-E2E-009 | Body type → listings?carType=New&bodyType= | PASS | navigateToBodyType sets query params
NC-E2E-010 | Body type Electric/Luxury supported on listings | FAIL | listings.bodyTypes lacks Electric/Luxury | Electric & Luxury body clicks filter to empty/incorrect
NC-E2E-011 | Above ₹30L means min≥30L | FAIL | uses maxPrice=100000000 (includes all) | Budget 'Above ₹30L' should set minPrice not max-all
NC-E2E-012 | View Details filters to model | FAIL | passes model QP but listings ignores it | Wire listings to read model QP or route to car detail
NC-E2E-013 | Compare button uses heart selection | FAIL | Compare link has no query/ids; heart state unused | Pass selected model IDs to /compare
NC-E2E-014 | Notify Me persists / emails user | FAIL | in-memory signal only | Persist notify + collect email/phone
NC-E2E-015 | Image error fallback path valid | FAIL | fallback=assets/placeholder.svg; exists=False; correct=assets/cars/placeholder.svg | Fix all fallbacks to assets/cars/placeholder.svg
NC-E2E-016 | Hotlinked aeplcdn images load | FAIL | ok=0 fail=6 of sampled | Replace hotlinks with owned CDN/assets; aeplcdn returns 404
NC-E2E-017 | New Launches 'last 3 months' accurate | FAIL | Includes May 2024 / Oct 2024 while subtitle claims last 3 months | Filter by real launch date or fix copy
NC-E2E-018 | NEW badge consistency | PARTIAL | Swift 2024 has isNew:false — explains missing badge | Decide badge rules; date pill truncation CSS
NC-E2E-019 | Expert View Model deep-links to model | FAIL | queryParams only make, not model | Pass make+model; ideally open model/variant page
NC-E2E-020 | Launch Explore deep-links to model | FAIL | only make QP | Pass model name too
NC-E2E-021 | Price range min≠max display | PARTIAL | UI shows ₹30L–₹30L when single variant price | Show '₹30.0L onwards' when min==max
NC-E2E-022 | View Details opens model/variant page | FAIL | Goes to /listings filter not /cars/:id | Use representativeId → /cars/:id or model page
NC-E2E-023 | Body type icons are vehicles | FAIL | Emoji/icons: SUV/MUV misleading in live UI | Replace with consistent car silhouette icons
NC-E2E-024 | Dedicated new-car search on page | PARTIAL | Hero brand/budget/body only; no free-text model search | Add model search box
NC-E2E-025 | AI recommendations on New Cars | FAIL | Expert picks hardcoded; no AI personalization | Wire to recommend API or label as editorial

## Screenshot Sections
Section (from user screenshots) | Status | Key findings
Browse by Body Type | PARTIAL | UI OK; Electric/Luxury not handled on listings; icons misleading
Browse by Budget | FAIL | Above ₹30L uses max=1Cr (shows almost all cars), not min≥30L
Popular New Car Models + Filters | FAIL | Most images broken; badge overlap; min=max price; Compare unwired
New Launches carousel | FAIL | CDN 404; 'last 3 months' false; date truncation; Swift missing NEW
Upcoming Cars + Notify Me | FAIL | Images broken; Notify is local signal only — no email/DB
Expert Recommendations | FAIL | Hardcoded; View Model only filters make, not model; not AI
Hero By Brand / Budget / Body | PASS | Tabs present and navigate with carType=New
Nav New Cars active + city Kolkata | PASS | Nav/chrome present in screenshots

## Gaps + Claude Prompt
Priority | Gap | Evidence | Fix
P0 | Hotlinked aeplcdn images return 404 | CDN probe + screenshots | Host images on own CDN/R2; stop third-party hotlinks
P0 | Fallback path assets/placeholder.svg missing | File not found; real is assets/cars/placeholder.svg | Fix all (error) handlers + src fallbacks
P0 | View Details ignores model query param | new-cars passes model; listings never reads params['model'] | On init: if make+model set selectedModel or go /cars/:id
P0 | Compare heart + Compare button unwired | compareSet unused; /compare has no prefill | Pass IDs via queryParams; hydrate compare slots
P0 | Notify Me not persisted | toggleNotify in-memory only | Save to Supabase/API + require auth/email
P0 | Budget Above ₹30L wrong | max=100000000 | Use minPrice=3000000 (and support minPrice on listings)
P0 | Electric/Luxury body types break filter | listings.bodyTypes lacks them | Map Electric→fuel=Electric; Luxury→minPrice; or add types
P1 | New Launches date copy false | May 2024 in 'last 3 months' | Compute window or change subtitle; fix date pill CSS overflow
P1 | Expert/Launch CTAs make-only | queryParams make only | Pass model; deep-link to variant list
P1 | Price range ₹30L–₹30L | min==max formatting | Show '₹X onwards' when single price
P1 | Card layout when image missing | Badge overlaps title | Fixed image aspect-ratio + reserved media box
P1 | Expert picks not AI / not data-driven | Hardcoded array | Editorial CMS or recommend API; label honestly
P1 | Body type iconography wrong | SUV graph / MUV person in UI | Use consistent vehicle icons/SVGs
P2 | No free-text model search on New Cars | Hero tabs only | Add search → listings q=
P2 | API seed has zero new listings | seed.py used-only | Seed new inventory for Next parity

## Claude Prompt
Fix ALL broken New Cars E2E features on Angular /new-cars (apps/gaadiiq-angular) based on docs/qa/NewCars-Full-E2E-Gaps.md and docs/qa/GAADIIQ_NewCars_Full_E2E_Results.xlsx. P0 — must fix: 1. IMAGES: Stop hotlinking imgd.aeplcdn.com (returns 404). Use owned assets under assets/cars/ or R2 CDN. Fix every image error fallback from assets/placeholder.svg → assets/cars/placeholder.svg. Reserve fixed aspect-ratio media box so badges never overlap titles. 2. VIEW DETAILS: From Popular Models, open the correct model variant view. Either (a) navigate to /listings?carType=New&make=&model= AND make listings.component read params['model'] to call selectModel(), or (b) routerLink to /cars/{{representativeId}}. 3. COMPARE: Wire compare-heart selections into /compare?ids=... (or session storage) and prefill compare slots. Compare button must not open empty compare. 4. NOTIFY ME: Persist upcoming-car notifications (Supabase table or API) with user email; require login; do not use only an in-memory signal. 5. BUDGET: Fix "Above ₹30L" to filter minPrice >= 3000000 (add minPrice query support on listings). Keep other budget chips as maxPrice. 6. BODY TYPE: Electric should filter fuel=Electric; Luxury should filter minPrice (e.g. 30L+). Do not send bodyType=Electric/Luxury into a bodyType enum that only has Hatchback/Sedan/SUV/MUV. P1: 7. New Launches: fix "last 3 months" filter/copy; fix date pill truncation; consistent NEW badge rules. 8. Expert Recommendations + Launch Explore: deep-link make+model (not make only). Label Expert as Editorial unless AI-backed. 9. Price display: if minPrice===maxPrice show "₹X.XL onwards". 10. Replace misleading body-type icons with vehicle SVGs. P2: Add model search on New Cars; keep Playwright/static regression cases. Acceptance: - No broken images on Popular Models / Launches / Upcoming (placeholder OK if real asset missing). - View Details lands on that model's variants. - Compare from heart pre-fills cars. - Notify Me survives refresh for logged-in user. - Above ₹30L and Electric/Luxury filters return sensible results. - Unit/e2e coverage for query-param wiring.