## Executive
GAADIIQ AI Diagnosis BRD QA
Generated | 2026-07-25 13:56 UTC
Code tip | claude/gaadiiq-app-dev-abj5fo
BRD Score | 63
Req PASS | 31
Req PARTIAL | 19
Req FAIL | 14
Test PASS | 23
Test PARTIAL | 6
Test FAIL | 18
Recommendation | NO-GO for full BRD; CONDITIONAL for manual+image MVP

## Requirements
ID | Area | Priority | Requirement | Status | Evidence | Gap | Justification
BR-VI-01 | Vehicle Info | Must Have | Manual vehicle information entry | PASS | Angular Step 1 form (make/model/year/fuel/transmission) | — | Baseline path for users who prefer typing
BR-VI-02 | Vehicle Info | Must Have | Voice-based vehicle information entry | PASS | voice-mode overlay + Web Speech STT | — | Hands-free capture for drivers / literacy barriers
BR-VI-03 | Vehicle Info | Must Have | Auto-extract vehicle details from speech | PASS | vehicle-info-extractor + POST /diagnosis/voice/extract | — | Reduce form friction after speech
BR-VI-04 | Vehicle Info | Must Have | Auto-fill of vehicle information | PASS | onVoiceCompleted merges into form signals | — | Keep single source of truth for review step
BR-VI-05 | Vehicle Info | Must Have | Intelligent validation | PASS | step1Valid + Pydantic DiagnoseRequest | — | Prevent invalid analyse payloads
BR-VI-06 | Vehicle Info | Must Have | Missing information prompts | PASS | voice-mode _askMissingFields TTS loop | — | Complete mandatory vehicle fields before analyse
BR-IR-01 | Issue Reporting | Must Have | Report issue using text | PASS | Step 2 textarea problem_description | — | Primary symptom capture
BR-IR-02 | Issue Reporting | Must Have | Report issue using voice | PASS | Step 2 mic toolbar + overlay problem phase | — | Speak symptoms in native language
BR-IR-03 | Issue Reporting | Must Have | Upload vehicle images | PASS | POST /upload/image → image_urls | — | Visual context for vision + mechanic handoff
BR-IR-04 | Issue Reporting | Must Have | Upload audio recordings | FAIL | DB/schema audio_url exists; unused | No POST /upload/audio or Step 2 UI | Engine noise / rattles improve diagnosis
BR-IR-05 | Issue Reporting | Must Have | Upload videos | FAIL | DB/schema video_url exists; unused | No video upload API/UI | Capture intermittent symptoms
BR-IR-06 | Issue Reporting | Must Have | Select dashboard warning lights | PASS | WARNING_LIGHTS chips in Step 2 | — | Structured symptom signals
BR-IR-07 | Issue Reporting | Should Have | Add maintenance history | FAIL | Not in form/API/model | Add maintenance_history JSON field | Prior service context
BR-ML-01 | Multilingual | Must Have | Automatic language detection | PARTIAL | detectLanguageFromText exists client-side | Wire Auto-detect toggle into voice session | Users may not know BCP-47 codes
BR-ML-02 | Multilingual | Must Have | Support major Indian languages | PASS | 11 VOICE_LANGUAGES in picker | PROMPTS fully localized for 6 only | India language coverage
BR-ML-03 | Multilingual | Must Have | Preserve user language in conversation | PASS | gq_voice_lang + detected_language | — | Consistent journey language
BR-ML-04 | Multilingual | Must Have | AI responses match user language | PARTIAL | _translate_diagnosis via Ollama | Golden-set QA; English fallback banner | Trust for non-English users
BR-VA-01 | Voice AI | Must Have | Speech-to-Text | PARTIAL | Browser Web Speech API only | Server STT + MediaRecorder for WebView | Production Android/iOS reliability
BR-VA-02 | Voice AI | Must Have | Text-to-Speech | PARTIAL | speechSynthesis only | Optional server TTS; keep client fallback | Playback on devices with weak voices
BR-VA-03 | Voice AI | Must Have | Live transcription | PASS | interimText in voice overlay | — | User confidence while speaking
BR-VA-04 | Voice AI | Should Have | Voice playback | PASS | Auto-speak report + TTS bar | — | Listen to diagnosis
BR-VA-05 | Voice AI | Should Have | Replay | PASS | replaySpeaking() | — | Re-hear instructions
BR-VA-06 | Voice AI | Should Have | Pause | PASS | pauseSpeaking() | — | Interruptible playback
BR-VA-07 | Voice AI | Should Have | Stop | PASS | stop STT/TTS controls | — | Immediate silence
BR-VA-08 | Voice AI | Should Have | Hands-free mode | PARTIAL | Auto-listen after TTS | Always-on driving mode | Parked/driving safety
BR-VA-09 | Voice AI | Should Have | Driver-friendly interaction | PARTIAL | Large overlay UI | Driving mode + RECORD_AUDIO | Large targets, reduced glances
BR-AI-01 | AI Diagnosis | Must Have | Ollama LLM integration | PASS | services/diagnosis.py run_diagnosis | — | Primary LLM path
BR-AI-02 | AI Diagnosis | Must Have | RAG knowledge base | PARTIAL | Keyword match on repair_knowledge.json (12 cases) | Vector RAG over KB (Qdrant/BGE unused) | Grounded repair advice
BR-AI-03 | AI Diagnosis | Must Have | Root cause prediction | PASS | possible_causes[] | — | Core diagnosis value
BR-AI-04 | AI Diagnosis | Must Have | Severity prediction | PASS | risk_level | — | Urgency signalling
BR-AI-05 | AI Diagnosis | Must Have | Safe-to-drive recommendation | PASS | safe_to_drive + UI warning | — | Safety-critical output
BR-AI-06 | AI Diagnosis | Must Have | Estimated repair cost | PASS | cost_min_inr / cost_max_inr | — | Budget transparency
BR-AI-07 | AI Diagnosis | Must Have | Estimated repair duration | PASS | repair_time_estimate | — | Time planning
BR-AI-08 | AI Diagnosis | Must Have | Recommended next steps | PASS | recommended_steps + How to Fix | — | Actionable guidance
BR-AI-09 | AI Diagnosis | Should Have | Preventive maintenance suggestions | PASS | preventive_maintenance | — | Upsell prevention
BR-AI-10 | AI Diagnosis | Should Have | Follow-up questions when required | PARTIAL | Missing-field asks only | Post-diagnosis follow_up_questions[] | Improve low-confidence cases
BR-UX-01 | UX | Must Have | Mobile-first design | PARTIAL | Responsive SCSS + layout e2e | Dedicated mobile shell polish | Primary usage is phone
BR-UX-02 | UX | Must Have | Progress indicators | PASS | Steps 1–3 wizard progress | — | Orient user in flow
BR-UX-03 | UX | Must Have | Conversation history | PARTIAL | Past Diagnoses panel + GET /history | No multi-turn conversation DB/UI; open-by-id weak | Revisit prior advice
BR-UX-04 | UX | Must Have | Voice/Text switching | PASS | Mode selector Step 1 | — | User preference
BR-UX-05 | UX | Must Have | Error handling | PASS | STT + diagnosis error cards | — | Recoverable failures
BR-UX-06 | UX | Should Have | Offline handling | PARTIAL | clientFallback when API down | Offline banner; STT needs network | Low-connectivity India
BR-SEC-01 | Security | Must Have | Microphone permissions | PARTIAL | Browser not-allowed string only | Android RECORD_AUDIO + Capacitor helper | OS-level mic access
BR-SEC-02 | Security | Must Have | Voice data encryption | PARTIAL | TLS in transit assumed | At-rest encryption design for recordings | Protect voice PII
BR-SEC-03 | Security | Must Have | Secure storage | PARTIAL | Postgres + R2 for images | Transcripts not stored securely | Controlled retention
BR-SEC-04 | Security | Must Have | User consent for voice processing | FAIL | Generic privacy pages only | Pre-STT consent modal (purpose/retention) | DPDP / lawful processing
BR-SEC-05 | Security | Must Have | Delete recordings | FAIL | Nothing voice-persisted yet | Retention + DELETE voice APIs | User control of biometric-adjacent data
BR-SEC-06 | Security | Must Have | Privacy compliance (DPDP) | PARTIAL | Disclaimer copy | Diagnosis/voice delete UX | India DPDP Act readiness
BR-PERF-01 | Performance | Must Have | Fast response time | PARTIAL | Heuristic fallback fast | Ollama timeout ≤8s → fallback | Perceived performance
BR-PERF-02 | Performance | Should Have | High STT accuracy | PARTIAL | Browser STT + noisy retry | WER benchmarks per language | Voice trust
BR-PERF-03 | Performance | Must Have | High AI response accuracy | PARTIAL | KB+Ollama | Golden-set fixtures in CI | Safety + usefulness
BR-API-01 | API | Must Have | STT API | FAIL | Browser-only | POST /diagnosis/stt (multipart) | WebView production path
BR-API-02 | API | Must Have | TTS API | FAIL | Browser-only | POST /diagnosis/tts optional | Consistent voice quality
BR-API-03 | API | Should Have | Language detection API | FAIL | Client-only heuristic | POST /diagnosis/detect-language | Server-side lang detect
BR-API-04 | API | Should Have | Translation API | PARTIAL | Internal _translate_diagnosis | Not standalone endpoint | Reuse across modules
BR-API-05 | API | Must Have | AI Diagnosis API | PASS | POST /diagnosis/analyse | — | Core backend
BR-API-06 | API | Must Have | Image upload API | PASS | POST /upload/image | — | Media pipeline
BR-API-07 | API | Must Have | Audio upload API | FAIL | Missing | POST /upload/audio | Persist engine audio
BR-DB-01 | Database | Must Have | Voice transcript storage | FAIL | Missing | voice_transcripts (consent-gated) | Audit + improve STT
BR-DB-02 | Database | Must Have | Conversation history storage | FAIL | In-session memory only | diagnosis_conversations | Multi-turn persistence
BR-DB-03 | Database | Must Have | AI diagnosis history | PASS | vehicle_diagnoses + Past Diagnoses UI | — | User revisit
BR-DB-04 | Database | Should Have | Audit logs | FAIL | Missing | diagnosis_audit_events | Compliance + debug
BR-TEST-01 | Quality | Must Have | Automated diagnosis tests | FAIL | No test_diagnosis.py / extractor specs | Add pytest + unit tests | Prevent regressions
BR-AND-01 | Mobile | Must Have | Android RECORD_AUDIO permission | FAIL | Manifest has CAMERA/location only | Add RECORD_AUDIO + runtime request | APK mic required

## TestCases
Suite | ID | Name | Status | Severity | Detail
Functional | TC-F-01 | Manual Step1→4 diagnose path | PASS | — | Wizard + analyse API
Functional | TC-F-02 | Voice language picker → capture vehicle | PASS | — | voice-mode flow
Functional | TC-F-03 | Extract Hindi/Bengali/Tamil brands | PASS | — | multilingual extractor
Functional | TC-F-04 | Missing field voice re-ask | PASS | — | _askMissingFields
Functional | TC-F-05 | Warning lights + severity | PASS | — | Step 2 chips
Functional | TC-F-06 | Image upload then analyse | PASS | — | upload + image_urls
Functional | TC-F-07 | Report cost/safe-drive/steps/disclaimer | PASS | — | Report UI
Functional | TC-F-08 | TTS play/pause/stop/replay | PASS | — | voice-diagnosis.service
Functional | TC-F-09 | Client KB fallback when API down | PASS | — | clientFallback
Functional | TC-F-10 | Auth history endpoint | PASS | — | GET /diagnosis/history
Functional | TC-F-11 | IDOR blocked on GET diagnosis | PASS | — | MOB-007 owner check
Functional | TC-F-12 | Upload audio recording | FAIL | P0 | No UI/API
Functional | TC-F-13 | Upload video | FAIL | P0 | No UI/API
Functional | TC-F-14 | Maintenance history entry | FAIL | P1 | Not implemented
Functional | TC-F-15 | Auto language detect without picker | FAIL | P1 | autoDetect unwired
Functional | TC-F-16 | Full prompt localization kn/ml/gu/pa/or | FAIL | P1 | PROMPTS only 6 langs
Functional | TC-F-17 | Angular Past Diagnoses history UI | PASS | — | history-panel on Claude tip
Functional | TC-F-18 | Server STT for WebView/Safari | FAIL | P0 | Browser STT only
Functional | TC-F-19 | Mic consent before STT | FAIL | P0 | Missing
Functional | TC-F-20 | Android RECORD_AUDIO declared | FAIL | P0 | Manifest gap
Functional | TC-F-21 | Persist conversation transcripts | FAIL | P1 | No DB
Functional | TC-F-22 | Delete voice data (DPDP) | FAIL | P1 | Missing
Functional | TC-F-23 | Post-diagnosis follow-up questions | FAIL | P2 | Not in analyse
Functional | TC-F-24 | Vector RAG for diagnosis KB | FAIL | P2 | Keyword only
Functional | TC-F-25 | Open past diagnosis by id from history | PARTIAL | P2 | List only; no detail navigation
Functional | TC-F-26 | Guest can analyse without login | PASS | — | Public analyse + rate limit
Functional | TC-F-27 | detected_language sent on analyse | PASS | — | Claude Angular + DiagnoseRequest
Security | TC-S-01 | Unauth GET diagnosis denied | PASS | — | owner auth
Security | TC-S-02 | Prompt injection fencing | PARTIAL | P0 | User text in prompts
Security | TC-S-03 | Rate limit analyse | PASS | — | documented limits
Security | TC-S-04 | Audio upload validation | FAIL | P1 | No audio upload
Security | TC-S-05 | Mic consent logged before STT | FAIL | P0 | No consent event
Performance | TC-P-01 | Analyse p95 with fallback | PARTIAL | P1 | Ollama unbounded
Performance | TC-P-02 | STT works offline | FAIL | P1 | Web Speech needs net
Performance | TC-P-03 | Image upload ≤10MB reject | PASS | — | upload validation path
A11y | TC-A-01 | Voice overlay SR labels | PARTIAL | P2 | Audit incomplete
A11y | TC-A-02 | aria-live for interim transcript | FAIL | P2 | Missing
Mobile | TC-M-01 | No horizontal overflow on route | PASS | — | mobile-layout e2e
Mobile | TC-M-02 | Voice overlay one-handed | PARTIAL | P2 | No driving mode
Regression | TC-R-01 | API pytest diagnosis suite | FAIL | P0 | No test_diagnosis.py
Regression | TC-R-02 | Voice extractor unit tests | FAIL | P0 | No *.spec.ts
Integration | TC-I-01 | Ollama down → heuristic report | PASS | — | fallback path
Integration | TC-I-02 | Vision on image_url | PARTIAL | P2 | vision.py untested quality
Integration | TC-I-03 | voice/extract then autofill | PASS | — | Claude tip path
Usability | TC-U-01 | Manual vs Voice mode clear | PASS | — | Step 1 selector
Usability | TC-U-02 | Disclaimer before submit | PASS | — | Step 3
Usability | TC-U-03 | safe_to_drive=false banner prominence | PASS | — | Report warning UI

## AcceptanceCriteria
Requirement ID | Status | Title
BR-VI-01 | PASS | Manual vehicle entry
BR-VI-02 | PASS | Voice vehicle entry
BR-VI-03 | PASS | Auto-extract from speech
BR-VI-04 | PASS | Auto-fill form
BR-VI-05 | PASS | Intelligent validation
BR-VI-06 | PASS | Missing info prompts
BR-IR-01 | PASS | Text issue report
BR-IR-02 | PASS | Voice issue report
BR-IR-03 | PASS | Image upload
BR-IR-04 | FAIL | Audio upload
BR-IR-05 | FAIL | Video upload
BR-IR-06 | PASS | Warning lights
BR-IR-07 | FAIL | Maintenance history
BR-ML-01 | PARTIAL | Auto language detect
BR-ML-02 | PASS | Indian languages
BR-ML-03 | PASS | Preserve language
BR-ML-04 | PARTIAL | AI language match
BR-VA-01 | PARTIAL | STT
BR-VA-02 | PARTIAL | TTS
BR-VA-03 | PASS | Live transcription
BR-VA-04 | PASS | Voice playback
BR-VA-05 | PASS | Replay
BR-VA-06 | PASS | Pause
BR-VA-07 | PASS | Stop
BR-VA-08 | PARTIAL | Hands-free
BR-VA-09 | PARTIAL | Driver-friendly
BR-AI-01 | PASS | Ollama
BR-AI-02 | PARTIAL | RAG KB
BR-AI-03 | PASS | Root cause
BR-AI-04 | PASS | Severity
BR-AI-05 | PASS | Safe-to-drive
BR-AI-06 | PASS | Repair cost
BR-AI-07 | PASS | Repair duration
BR-AI-08 | PASS | Next steps
BR-AI-09 | PASS | Preventive
BR-AI-10 | PARTIAL | Follow-ups
BR-UX-01 | PARTIAL | Mobile-first
BR-UX-02 | PASS | Progress
BR-UX-03 | PARTIAL | Conversation history
BR-UX-04 | PASS | Voice/Text switch
BR-UX-05 | PASS | Error handling
BR-UX-06 | PARTIAL | Offline
BR-SEC-01 | PARTIAL | Mic permissions
BR-SEC-02 | PARTIAL | Voice encryption
BR-SEC-03 | PARTIAL | Secure storage
BR-SEC-04 | FAIL | Mic consent
BR-SEC-05 | FAIL | Delete recordings
BR-SEC-06 | PARTIAL | DPDP
BR-PERF-01 | PARTIAL | Fast response
BR-PERF-02 | PARTIAL | STT accuracy
BR-PERF-03 | PARTIAL | AI accuracy
BR-API-01 | FAIL | STT API
BR-API-02 | FAIL | TTS API
BR-API-03 | FAIL | Lang detect API
BR-API-04 | PARTIAL | Translation API
BR-API-05 | PASS | Diagnosis API
BR-API-06 | PASS | Image upload API
BR-API-07 | FAIL | Audio upload API
BR-DB-01 | FAIL | Transcript storage
BR-DB-02 | FAIL | Conversation storage
BR-DB-03 | PASS | Diagnosis history
BR-DB-04 | FAIL | Audit logs
BR-TEST-01 | FAIL | Automated tests
BR-AND-01 | FAIL | Android RECORD_AUDIO