## Executive
GAADIIQ — Car Image Asset Management BRD QA
Generated | 2026-08-02 06:57 UTC
Code tip | claude/gaadiiq-app-dev-abj5fo @ 0b0bb10
BRD readiness score | 55
Requirements PASS | 11
Requirements PARTIAL | 21
Requirements FAIL | 7
Test PASS | 15
Test PARTIAL | 2
Test FAIL | 15
Total requirements | 39
Total test cases | 32
Verdict | NO-GO for full BRD; API DAM foundation Conditional; UI P0
Live UX bug | File Ingestion accepts images → API 'File is not a PDF'
P0 fix | Build /admin/car-images → /media-admin; fix PDF page accept/copy

## Requirements
ID | Area | Priority | Requirement | Status | Evidence | Gap
BR-001 | Upload | Must Have | Multi image upload JPG/JPEG/PNG/WEBP/HEIC/TIFF; configurable max up to 15GB | PARTIAL | POST /media-admin/upload + sniff_image; media_max_upload_mb default 64MB | No Angular UI; no 15GB/chunked path; HEIC/TIFF not browser-converted
BR-002 | Metadata | Must Have | Mandatory make/model/year/body/fuel/transmission/category; optional variant/color/primary | PARTIAL | API form fields on media-admin upload | No admin metadata form UI; body_type naming differs
BR-003 | Categories | Must Have | Full image category vocabulary (exterior/interior/360/etc.) | PASS | ImageCategory enum in vehicle_media.py | Videos future — enum has video value
BR-004 | AI Extract | Must Have | AI extract from filename/EXIF; admin editable before save | PARTIAL | filename_metadata + POST /media-admin/inspect; PATCH after save | EXIF never populated; no pre-save review UI
BR-005 | Storage Meta | Must Have | Rich metadata: hash, thumb, resolution, SEO, embedding, OCR, copyright… | PARTIAL | vehicle_media: hash/phash/thumb/w/h/alt/seo/copyright columns | OCR, embedding vector, EXIF fill, AI description generation missing
BR-DB-01 | Database | Must Have | Manufacturers / Models / Variants / CarImages relational tables | FAIL | Flat cars + vehicle_media free-text tags | No BRD hierarchy tables; design-only in LLD
BR-STO-01 | Storage | Must Have | Path /car-images/{make}/{model}/{year}/{category}/; no duplicate bytes | PARTIAL | car-images/{make}/{model}/{year}/{hash}.ext + sha256/phash dedupe | Category folder segment missing
BR-DSP-01 | Display | Must Have | Manufacturer page auto-display from single source | PARTIAL | GET /brochures/images + VehicleImageService on New Cars | No dedicated manufacturer page DAM wiring everywhere
BR-DSP-02 | Display | Must Have | Model page auto-display | PARTIAL | New Cars / car detail / brochure gallery | Incomplete vs all model surfaces
BR-DSP-03 | Display | Must Have | Variant page auto-display | PARTIAL | Filterable via media query params | Variant-specific surfaces incomplete
BR-DSP-04 | Display | Must Have | Search / AI Advisor / Compare / Dealer reuse same asset | PARTIAL | Compare + cards wired; AI Advisor & Dealer not | Wire Advisor + Dealer to vehicle_media
BR-SRCH-01 | Search | Should Have | Smart search: make/model/color/view filters | PARTIAL | OpenSearch media index + GET images filters | Semantic 'White Nexon Front View' natural language incomplete
BR-AI-01 | AI Features | Should Have | Auto-tag, dedupe, compress, thumb, SEO alt, description, semantic search, OCR, quality, moderation | PARTIAL | Dedupe + thumb + alt fields; filename tag | OCR/embeddings/moderation/blur/quality gates missing
FR-001 | Functional | Must Have | Admin multi-image upload | PASS | API + TestMultipleUploadSuite | No Angular Car Image Admin UI
FR-002 | Functional | Must Have | Mandatory metadata validation before save | PASS | API TestMandatoryMetadataSuite | UI missing
FR-003 | Functional | Must Have | AI auto-populates metadata | PARTIAL | Filename inspect only | EXIF/vision auto-tag missing
FR-004 | Functional | Must Have | Admin can override AI values | PASS | PATCH /media-admin/{id} | Pre-save override UI missing
FR-005 | Functional | Must Have | Images stored once in cloud | PASS | content_hash dedupe in media_library | —
FR-006 | Functional | Must Have | Same image reused across surfaces | PARTIAL | Shared vehicle_media read path | Advisor/Dealer not wired
FR-007 | Functional | Must Have | Automatic thumbnail generation | PASS | pdf_ingest thumb path used by media library | —
FR-008 | Functional | Should Have | Automatic WebP conversion | FAIL | Original format mostly kept | Add convert-to-WebP pipeline
FR-009 | Functional | Must Have | Duplicate detection before save | PASS | sha256 + phash dedupe | —
FR-010 | Functional | Should Have | Version history for image updates | FAIL | No media version table | Add vehicle_media_versions
NFR-001 | NFR | Must Have | Support uploads up to 15 GB | FAIL | Default 64MB; comment notes chunked needed | Resumable/chunked upload
NFR-002 | NFR | Must Have | Upload response ≤10s for standard images | FAIL | No SLA assertion/monitoring | Add perf test + timeout policy
NFR-003 | NFR | Must Have | CDN integration | PARTIAL | S3/R2 public_base support | Default local /media paths in many envs
NFR-004 | NFR | Must Have | RBAC for admin upload | PASS | get_admin_user on media-admin + brochures | Dev shortcut localOnly has no token (ops issue)
NFR-005 | NFR | Should Have | Audit logging for uploads/modifications | PARTIAL | Basic logging | Dedicated audit table incomplete
AC-001 | Acceptance | Must Have | Admin can upload one or multiple car images | PARTIAL | API PASS; UI FAIL | Build Car Image Admin UI
AC-002 | Acceptance | Must Have | Mandatory fields validated before save | PASS | API 422 on missing fields | Surface validation in UI
AC-003 | Acceptance | Must Have | AI extracts metadata from filename/image meta | PARTIAL | Filename inspect PASS; EXIF FAIL | Populate EXIF + UI prefill
AC-004 | Acceptance | Must Have | Admin review/modify AI metadata before save | FAIL | Only post-save PATCH | Inspect → edit grid → upload flow in UI
AC-005 | Acceptance | Must Have | Stored once and linked via metadata | PASS | Dedupe + vehicle_media links | —
AC-006 | Acceptance | Must Have | Appear on Manufacturer/Model/Variant without re-upload | PARTIAL | Partial surface wiring | Complete all pages
AC-007 | Acceptance | Must Have | Search shows correct images by metadata filters | PARTIAL | GET /brochures/images filters | NL semantic search
AC-008 | Acceptance | Must Have | Duplicate uploads detected and flagged | PASS | deduplicated=1 API behavior + tests | —
AC-009 | Acceptance | Must Have | Thumbnails and optimized formats auto-generated | PARTIAL | Thumbs yes; WebP optimize no | WebP conversion
AC-010 | Acceptance | Should Have | Metadata supports SEO/AI search/analytics | PARTIAL | alt/seo columns exist | Embeddings + analytics events
UX-001 | UX Bug | Must Have | Admin File Ingestion must not claim image upload if PDF-only | FAIL | /admin/pdf-ingestion accept=*/* then API 'File is not a PDF' | Separate Car Image Admin OR route images to /media-admin

## TestCases
Suite | ID | Name | Status | Severity | BR Ref | Detail
Functional | TC-IMG-001 | Multi PNG upload via /media-admin/upload with mandatory fields | PASS | — | FR-001/AC-001 | API + TestMultipleUploadSuite
Functional | TC-IMG-002 | Accept JPG/JPEG/PNG/WEBP/HEIC/TIFF by magic bytes | PASS | — | BR-001 | sniff_image allowlist
Functional | TC-IMG-003 | Reject non-image masquerading as .jpg | PASS | — | BR-001 | 422 magic-byte reject
Functional | TC-IMG-004 | Missing make/model/year rejected | PASS | — | AC-002 | TestMandatoryMetadataSuite
Functional | TC-IMG-005 | Invalid image_category rejected with vocabulary | PASS | — | BR-003 | ImageCategory enum
Functional | TC-IMG-006 | Inspect Tata_Nexon_FearlessPlus_Front_2025.webp filename | PASS | — | AC-003 | filename_metadata + /inspect
Functional | TC-IMG-007 | PATCH metadata after upload | PASS | — | FR-004 | PATCH /media-admin/{id}
Functional | TC-IMG-008 | Duplicate bytes → deduplicated flag | PASS | — | AC-008 | sha256/phash
Functional | TC-IMG-009 | Storage key includes {category} folder | FAIL | P1 | BR-STO-01 | Key omits category segment
Functional | TC-IMG-010 | Upload 100MB with default config | FAIL | P1 | NFR-001 | Default cap 64MB
Functional | TC-IMG-011 | Configure MEDIA_MAX_UPLOAD_MB raises limit | PARTIAL | P1 | BR-001 | Config works; not 15GB/chunked
UI | TC-IMG-012 | Angular Car Image Admin multi-select + metadata grid | FAIL | P0 | AC-001/AC-004 | No /media-admin UI; only PDF page
UI | TC-IMG-013 | File Ingestion upload JPG as car image | FAIL | P0 | UX-001 | API returns File is not a PDF
UI | TC-IMG-014 | File Ingestion upload PDF brochure | PASS | — | Separate feature | brochures/upload PDF path
AI | TC-IMG-015 | EXIF make/model auto-fill | FAIL | P1 | BR-004 | EXIF column never populated
AI | TC-IMG-016 | OCR text stored on media row | FAIL | P2 | BR-AI-01 | Not implemented for car images
AI | TC-IMG-017 | Image embedding vector for semantic search | FAIL | P2 | AC-010 | Not on vehicle_media
Integration | TC-IMG-018 | New Cars card uses vehicle_media when car.image empty | PASS | — | BR-DSP-02 | VehicleImageService.imageFor
Integration | TC-IMG-019 | Compare uses shared media library | PASS | — | FR-006 | compare + brochure images
Integration | TC-IMG-020 | AI Advisor uses shared media library | FAIL | P0 | BR-DSP-04 | Still placeholders/car.image
Integration | TC-IMG-021 | Dealer dashboard uses shared media | FAIL | P1 | BR-DSP-04 | Not wired
Integration | TC-IMG-022 | GET /brochures/images filter make/model/variant | PASS | — | AC-007 | Shared read API
Performance | TC-IMG-023 | 5MB image upload p95 ≤10s | FAIL | P2 | NFR-002 | No SLA test/monitor
Infrastructure | TC-IMG-024 | CDN public URL when R2 configured | PARTIAL | P2 | NFR-003 | S3Storage public_base
Security | TC-IMG-025 | Unauthenticated media-admin upload → 401 | PASS | — | NFR-004 | get_admin_user
Security | TC-IMG-026 | Non-admin token → 403 | PASS | — | NFR-004 | admin dependency
Regression | TC-IMG-027 | pytest test_media_admin suite green | PASS | — | FR-* | Exists on tip
UX | TC-IMG-028 | Pre-save AI metadata review grid | FAIL | P0 | AC-004 | No inspect→edit→upload UI
Data | TC-IMG-029 | Manufacturers/Models/Variants/CarImages tables exist | FAIL | P1 | BR-DB-01 | Not as BRD specifies
Functional | TC-IMG-030 | Automatic WebP conversion on store | FAIL | P1 | FR-008 | Not implemented
Functional | TC-IMG-031 | Image version history on replace | FAIL | P2 | FR-010 | No versions table
UI | TC-IMG-032 | Nav label 'Car Image Management' vs File Ingestion only | FAIL | P1 | UX-001 | Navbar only File Ingestion

## Gaps_P0_P1_P2
Priority | ID | Gap | Suggested fix
P0 | UX-001 | File Ingestion UI accepts images; API PDF-only → File is not a PDF | Add /admin/car-images OR route images to /media-admin; fix accept/copy
P0 | AC-001/012 | No Angular Car Image Admin for /media-admin | Build inspect→edit→upload UI
P0 | AC-004 | No pre-save AI metadata review | Metadata grid before upload
P0 | BR-DSP-04 | AI Advisor not on shared media | Use VehicleImageService / brochures images
P1 | BR-STO-01 | Storage path missing {category} | Include category in object key
P1 | NFR-001 | 15GB not supported (64MB default) | Chunked upload or revise BRD max
P1 | BR-004 | EXIF not populated | Parse EXIF in inspect/upload
P1 | FR-008 | No WebP conversion | Generate WebP derivative
P1 | BR-DB-01 | No Manufacturers/Models/Variants/CarImages tables | FK model or document free-text approach
P1 | TC-IMG-021 | Dealer dashboard not wired | Shared media in dealer UI
P2 | FR-010 | No version history | vehicle_media_versions
P2 | AC-010 | No image embeddings | Vector column + semantic search
P2 | NFR-002 | No ≤10s SLA test | Perf fixture in CI

## AcceptanceCriteria
AC ID | Criteria | Status | Notes
AC-001 | Admin can upload one or multiple car images | PARTIAL | Build Car Image Admin UI
AC-002 | Mandatory fields validated before save | PASS | Surface validation in UI
AC-003 | AI extracts metadata from filename/image meta | PARTIAL | Populate EXIF + UI prefill
AC-004 | Admin review/modify AI metadata before save | FAIL | Inspect → edit grid → upload flow in UI
AC-005 | Stored once and linked via metadata | PASS | —
AC-006 | Appear on Manufacturer/Model/Variant without re-upload | PARTIAL | Complete all pages
AC-007 | Search shows correct images by metadata filters | PARTIAL | NL semantic search
AC-008 | Duplicate uploads detected and flagged | PASS | —
AC-009 | Thumbnails and optimized formats auto-generated | PARTIAL | WebP conversion
AC-010 | Metadata supports SEO/AI search/analytics | PARTIAL | Embeddings + analytics events